## Activity Templates
Template Name | Project Type | Entity Code | Brand Code | Project Name | Store Class | Row Key | Parent Row Key | Activity | Activity Mode | Milestone | Milestone Order | Milestone Weight % | Activity Weight % | Sub-Task Weight % | Acceptance Criteria | Asset Item | Model Specs | Quantity | Responsible | Department | Sub Unit | Duration Days | Order | Requisite Row Key | Can Run Parallel
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A01 |  | Rollout Preparation | Standard | Three-Store Process Review | 1 | 100 | 15 |  | Rollout Preparation is completed and accepted. |  |  | 1 | Project Manager |  |  | 3 | 1 |  | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A01-S01 | M01-A01 | Confirm rollout scope, target count, waves, and owners | Standard | Three-Store Process Review | 1 | 100 | 15 | 33.33 | Approved rollout register identifies scope, waves, owners, and target count. |  |  | 1 | Project Manager |  |  | 1 | 2 |  | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A01-S02 | M01-A01 | Approve readiness checklist and support model | Standard | Three-Store Process Review | 1 | 100 | 15 | 33.33 | Entry criteria, escalation path, support coverage, and evidence requirements are approved. |  |  | 1 | Project Manager |  |  | 1 | 3 | M01-A01-S01 | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A01-S03 | M01-A01 | Confirm deployment package and rollback procedure | Standard | Three-Store Process Review | 1 | 100 | 15 | 33.34 | A tested deployment package and rollback procedure are available. |  |  | 1 | Project Manager |  |  | 1 | 4 | M01-A01-S02 | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A02 |  | Store Deployment | Per Store | Three-Store Process Review | 1 | 100 | 70 |  | Store Deployment is completed and accepted. |  |  | 1 | Deployment Team |  |  | 5 | 5 | M01-A01 | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A02-S01 | M01-A02 | Schedule process-review workshop | Per Store | Three-Store Process Review | 1 | 100 | 70 | 20 | Store participants and review schedule are confirmed. |  |  | 1 | Deployment Team |  |  | 1 | 6 | M01-A01 | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A02-S02 | M01-A02 | Document current process and evidence | Per Store | Three-Store Process Review | 1 | 100 | 70 | 20 | Actual process, controls, reports, and exceptions are documented. |  |  | 1 | Deployment Team |  |  | 1 | 7 | M01-A02-S01 | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A02-S03 | M01-A02 | Assess gaps against DAVID target process | Per Store | Three-Store Process Review | 1 | 100 | 70 | 20 | Gaps, impacts, risks, and owners are recorded. |  |  | 1 | Deployment Team |  |  | 1 | 8 | M01-A02-S02 | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A02-S04 | M01-A02 | Agree corrective actions and target dates | Per Store | Three-Store Process Review | 1 | 100 | 70 | 20 | Actions have accountable owners and accepted target dates. |  |  | 1 | Deployment Team |  |  | 1 | 9 | M01-A02-S03 | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A02-S05 | M01-A02 | Approve store review and closure status | Per Store | Three-Store Process Review | 1 | 100 | 70 | 20 | Store and process owner approve the review outcome. |  |  | 1 | Deployment Team |  |  | 1 | 10 | M01-A02-S04 | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A03 |  | Stabilization and Closure | Standard | Three-Store Process Review | 1 | 100 | 15 |  | Stabilization and Closure is completed and accepted. |  |  | 1 | Project Manager / Support Team |  |  | 3 | 11 | M01-A02 | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A03-S01 | M01-A03 | Monitor rollout KPIs and outstanding store issues | Standard | Three-Store Process Review | 1 | 100 | 15 | 33.33 | Completion, failure, and issue trends are current and actionable. |  |  | 1 | Project Manager / Support Team |  |  | 1 | 12 | M01-A02 | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A03-S02 | M01-A03 | Resolve priority deployment issues | Standard | Three-Store Process Review | 1 | 100 | 15 | 33.33 | No unresolved rollout blocker remains. |  |  | 1 | Project Manager / Support Team |  |  | 1 | 13 | M01-A03-S01 | No
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | Both | M01-A03-S03 | M01-A03 | Reconcile completed stores against target and close wave | Standard | Three-Store Process Review | 1 | 100 | 15 | 33.34 | Accepted stores reconcile to the rollout register and the sponsor approves closure. |  |  | 1 | Project Manager / Support Team |  |  | 1 | 14 | M01-A03-S02 | No

## Template Index
Included Hybrid SDLC / Agile Templates
Template Name | Project Type | Entity | Brand | Project Name | Milestones | Import Rows
TGI - DSY - DAVID - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | DSY | DAVID | 1 | 14

## Instructions
Hybrid SDLC / Agile Activity Template Instructions
Purpose | Recommended starting structures for the listed application projects. Review owners, durations, dependencies, weights, and acceptance criteria before importing.
Import | Open Activity Templates, choose Import, and upload this XLSX. The application groups rows by Template Name, Project Type, and Store Class.
Project Name | DAVID, LINK HUB, DIWA, and LINK PORTAL remain plain-text Project Name values; there is no Solution dropdown.
Hierarchy | Milestone = business capability or release; Activity = SDLC phase, sprint, or store rollout; Sub-Task = assignable accepted deliverable.
All Departments | All Departments' Process Implementation in LINK HUB contains one Activity per business process. Its Sub-Tasks cover department readiness plus the hybrid SDLC / Agile work needed to implement, test, release, and adopt that process in LINK HUB.
Collaboration Matrix | Use the matrix as the cross-department reporting view. Milestone marks the primary owning department and Waiting is the recommended initial state; replace these with current status or target week as planning progresses. Imported Sub-Tasks remain the source of progress percentages.
Parallel planning | Independent departmental readiness checkpoints run in parallel after the target workflow is approved. LINK HUB business processes also run as parallel workstreams; design/build/QA/UAT/release gates inside each process remain sequential.
Task Board | Keep detailed user stories, bugs, and developer tasks on the Task Board. The Gantt should track accepted sprint/release outcomes.
Weights | Milestones total 100% per template, activities total 100% per milestone, and sub-tasks total 100% per activity.
Per Store | A Per Store activity is cloned after target stores are selected. Do not manually create 35 placeholder store rows.
NONOS DIWA | 35 is the recommended target-store count. The workbook does not create store assignments.
CBTL DIWA | Target-store count remains to be confirmed.
Safety | Import into a test environment first. Re-importing an identical template is skipped rather than overwriting it.

## WBS Guide
Work-Breakdown Guide
Level | Use | Example | Progress rule
Project | One application in one entity/brand context | DAVID · TGI · CBTL | Weighted milestone roll-up
Milestone | Business capability, release, or rollout outcome | Inventory Scanning with Barcode Scanner | Weighted activity roll-up
Activity | SDLC phase, Agile sprint, or per-store deployment | Sprint 1 – Core Workflow | Weighted sub-task roll-up
Sub-Task | Concrete deliverable with acceptance criteria | Product owner accepts sprint demo | Owner updates 0–100%
Task Board | Stories, bugs, coding tasks, and daily execution | API validation bug | Feeds its linked Gantt deliverable

## Lists (hidden)
Project Types | Entity Codes | Brand Codes | Store Classes | Activity Modes | Yes / No
Full Service Group: Customer Brand | TGI | NONOS | Regular | Standard | No
Corporate Group: Servicing Brand | GSI | CBTL | Kitchen | Per Store | Yes
| NCF | DSY | Both
DBS