## Activity Templates
Template Name | Project Type | Entity Code | Brand Code | Project Name | Store Class | Row Key | Parent Row Key | Activity | Activity Mode | Milestone | Milestone Order | Milestone Weight % | Activity Weight % | Sub-Task Weight % | Acceptance Criteria | Asset Item | Model Specs | Quantity | Responsible | Department | Sub Unit | Duration Days | Order | Requisite Row Key | Can Run Parallel
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A01 |  | Rollout Preparation | Standard | POS Agent Deployment | 1 | 50 | 15 |  | Rollout Preparation is completed and accepted. |  |  | 1 | Project Manager |  |  | 3 | 1 |  | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A01-S01 | M01-A01 | Confirm rollout scope, target count, waves, and owners | Standard | POS Agent Deployment | 1 | 50 | 15 | 33.33 | Approved rollout register identifies scope, waves, owners, and target count. |  |  | 1 | Project Manager |  |  | 1 | 2 |  | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A01-S02 | M01-A01 | Approve readiness checklist and support model | Standard | POS Agent Deployment | 1 | 50 | 15 | 33.33 | Entry criteria, escalation path, support coverage, and evidence requirements are approved. |  |  | 1 | Project Manager |  |  | 1 | 3 | M01-A01-S01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A01-S03 | M01-A01 | Confirm deployment package and rollback procedure | Standard | POS Agent Deployment | 1 | 50 | 15 | 33.34 | A tested deployment package and rollback procedure are available. |  |  | 1 | Project Manager |  |  | 1 | 4 | M01-A01-S02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A02 |  | Store Deployment | Per Store | POS Agent Deployment | 1 | 50 | 70 |  | Store Deployment is completed and accepted. |  |  | 1 | Deployment Team |  |  | 5 | 5 | M01-A01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A02-S01 | M01-A02 | Confirm store schedule, owner, and prerequisites | Per Store | POS Agent Deployment | 1 | 50 | 70 | 20 | Store, support owner, deployment window, device, network, and access prerequisites are confirmed. |  |  | 1 | Deployment Team |  |  | 1 | 6 | M01-A01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A02-S02 | M01-A02 | Install and authenticate POS Agent | Per Store | POS Agent Deployment | 1 | 50 | 70 | 20 | The approved agent version is installed and securely authenticated. |  |  | 1 | Deployment Team |  |  | 1 | 7 | M01-A02-S01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A02-S03 | M01-A02 | Complete initial synchronization | Per Store | POS Agent Deployment | 1 | 50 | 70 | 20 | Required master and transaction data synchronize without blocking errors. |  |  | 1 | Deployment Team |  |  | 1 | 8 | M01-A02-S02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A02-S04 | M01-A02 | Execute end-to-end POS validation | Per Store | POS Agent Deployment | 1 | 50 | 70 | 20 | Critical POS scenarios pass and evidence is recorded. |  |  | 1 | Deployment Team |  |  | 1 | 9 | M01-A02-S03 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A02-S05 | M01-A02 | Brief users and obtain store acceptance | Per Store | POS Agent Deployment | 1 | 50 | 70 | 20 | Store users understand support procedures and the accountable manager accepts deployment. |  |  | 1 | Deployment Team |  |  | 1 | 10 | M01-A02-S04 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A03 |  | Stabilization and Closure | Standard | POS Agent Deployment | 1 | 50 | 15 |  | Stabilization and Closure is completed and accepted. |  |  | 1 | Project Manager / Support Team |  |  | 3 | 11 | M01-A02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A03-S01 | M01-A03 | Monitor rollout KPIs and outstanding store issues | Standard | POS Agent Deployment | 1 | 50 | 15 | 33.33 | Completion, failure, and issue trends are current and actionable. |  |  | 1 | Project Manager / Support Team |  |  | 1 | 12 | M01-A02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A03-S02 | M01-A03 | Resolve priority deployment issues | Standard | POS Agent Deployment | 1 | 50 | 15 | 33.33 | No unresolved rollout blocker remains. |  |  | 1 | Project Manager / Support Team |  |  | 1 | 13 | M01-A03-S01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M01-A03-S03 | M01-A03 | Reconcile completed stores against target and close wave | Standard | POS Agent Deployment | 1 | 50 | 15 | 33.34 | Accepted stores reconcile to the rollout register and the sponsor approves closure. |  |  | 1 | Project Manager / Support Team |  |  | 1 | 14 | M01-A03-S02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A01 |  | Discovery and Backlog | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 |  | Discovery and Backlog is completed and accepted. |  |  | 1 | Business Analyst |  |  | 3 | 15 | M01-A03 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A01-S01 | M02-A01 | Confirm stakeholders, product owner, KPIs, and scope | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 | 33.33 | Stakeholders, accountable owner, measurable KPIs, scope, and exclusions are documented and accepted. |  |  | 1 | Business Analyst |  |  | 1 | 16 | M01-A03 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A01-S02 | M02-A01 | Document current and target process | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 | 33.33 | The approved as-is and to-be flows identify actors, rules, exceptions, and hand-offs. |  |  | 1 | Business Analyst |  |  | 1 | 17 | M02-A01-S01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A01-S03 | M02-A01 | Create and approve prioritized backlog | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 | 33.34 | Epics and acceptance-ready stories are prioritized for the release. |  |  | 1 | Business Analyst |  |  | 1 | 18 | M02-A01-S02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A02 |  | Solution Design and Release Planning | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 |  | Solution Design and Release Planning is completed and accepted. |  |  | 1 | Product Owner / Technical Lead |  |  | 3 | 19 | M02-A01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A02-S01 | M02-A02 | Complete functional and UX design | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 | 33.33 | Business rules, screens, validations, and user journeys are approved. |  |  | 1 | Product Owner / Technical Lead |  |  | 1 | 20 | M02-A01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A02-S02 | M02-A02 | Complete architecture, security, and integration design | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 | 33.33 | Technical design covers interfaces, data, access, audit, and non-functional requirements. |  |  | 1 | Product Owner / Technical Lead |  |  | 1 | 21 | M02-A02-S01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A02-S03 | M02-A02 | Approve estimates, sprint plan, and release plan | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 | 33.34 | Capacity, sprint goals, dependencies, risks, and release criteria are baselined. |  |  | 1 | Product Owner / Technical Lead |  |  | 1 | 22 | M02-A02-S02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A03 |  | Sprint 0 - Foundation | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 5 |  | Sprint 0 - Foundation is completed and accepted. |  |  | 1 | Development Team |  |  | 3 | 23 | M02-A02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A03-S01 | M02-A03 | Prepare environments and delivery pipeline | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 5 | 33.33 | Development and test environments and deployment pipeline are usable. |  |  | 1 | Development Team |  |  | 1 | 24 | M02-A02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A03-S02 | M02-A03 | Create technical foundation and feature controls | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 5 | 33.33 | Required scaffolding, configuration, access, and feature controls are implemented. |  |  | 1 | Development Team |  |  | 1 | 25 | M02-A03-S01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A03-S03 | M02-A03 | Review Sprint 0 increment | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 5 | 33.34 | The team demonstrates the foundation and closes blocking findings. |  |  | 1 | Development Team |  |  | 1 | 26 | M02-A03-S02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A04 |  | Sprint 1 - Core Workflow | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 20 |  | Sprint 1 - Core Workflow is completed and accepted. |  |  | 1 | Scrum Team |  |  | 3 | 27 | M02-A03 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A04-S01 | M02-A04 | Deliver highest-priority workflow stories | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 20 | 33.33 | Committed core stories meet their acceptance criteria and code-review standards. |  |  | 1 | Scrum Team |  |  | 1 | 28 | M02-A03 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A04-S02 | M02-A04 | Execute developer and component tests | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 20 | 33.33 | Automated and manual component tests pass with evidence. |  |  | 1 | Scrum Team |  |  | 1 | 29 | M02-A04-S01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A04-S03 | M02-A04 | Hold sprint review and accept increment | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 20 | 33.34 | The product owner accepts the sprint goal or records follow-up backlog items. |  |  | 1 | Scrum Team |  |  | 1 | 30 | M02-A04-S02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A05 |  | Sprint 2 - Integration and Refinement | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 |  | Sprint 2 - Integration and Refinement is completed and accepted. |  |  | 1 | Scrum Team |  |  | 3 | 31 | M02-A04 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A05-S01 | M02-A05 | Deliver integrations, exceptions, and remaining release stories | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 | 33.33 | Committed integration and exception-path stories meet acceptance criteria. |  |  | 1 | Scrum Team |  |  | 1 | 32 | M02-A04 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A05-S02 | M02-A05 | Complete regression and defect correction | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 | 33.33 | Release-scope regression passes and critical sprint defects are closed. |  |  | 1 | Scrum Team |  |  | 1 | 33 | M02-A05-S01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A05-S03 | M02-A05 | Hold sprint review and freeze release scope | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 | 33.34 | The product owner accepts the increment and confirms the release candidate scope. |  |  | 1 | Scrum Team |  |  | 1 | 34 | M02-A05-S02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A06 |  | Integrated Quality Assurance | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 |  | Integrated Quality Assurance is completed and accepted. |  |  | 1 | QA Team |  |  | 3 | 35 | M02-A05 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A06-S01 | M02-A06 | Execute functional, integration, and regression testing | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 | 33.33 | Approved test cases pass and results are traceable to requirements. |  |  | 1 | QA Team |  |  | 1 | 36 | M02-A05 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A06-S02 | M02-A06 | Validate permissions, audit, performance, and security | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 | 33.33 | Applicable non-functional controls pass without release-blocking findings. |  |  | 1 | QA Team |  |  | 1 | 37 | M02-A06-S01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A06-S03 | M02-A06 | Close release-blocking defects and issue QA exit | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 | 33.34 | No unresolved release blocker remains and QA exit is approved. |  |  | 1 | QA Team |  |  | 1 | 38 | M02-A06-S02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A07 |  | UAT and Operational Readiness | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 |  | UAT and Operational Readiness is completed and accepted. |  |  | 1 | Product Owner / Key Users |  |  | 3 | 39 | M02-A06 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A07-S01 | M02-A07 | Prepare UAT scenarios, users, and representative data | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 | 33.33 | UAT coverage, users, environment, and data are ready. |  |  | 1 | Product Owner / Key Users |  |  | 1 | 40 | M02-A06 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A07-S02 | M02-A07 | Conduct UAT and resolve business findings | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 | 33.33 | Business scenarios pass and blocking findings are closed or formally accepted. |  |  | 1 | Product Owner / Key Users |  |  | 1 | 41 | M02-A07-S01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A07-S03 | M02-A07 | Complete SOP, training, support, and business sign-off | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 15 | 33.34 | Users and support teams are prepared and the process owner signs acceptance. |  |  | 1 | Product Owner / Key Users |  |  | 1 | 42 | M02-A07-S02 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A08 |  | Release and Hypercare | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 |  | Release and Hypercare is completed and accepted. |  |  | 1 | Release Manager |  |  | 3 | 43 | M02-A07 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A08-S01 | M02-A08 | Approve deployment and rollback readiness | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 | 33.33 | Go/no-go participants approve the production and rollback plan. |  |  | 1 | Release Manager |  |  | 1 | 44 | M02-A07 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A08-S02 | M02-A08 | Deploy and complete production smoke tests | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 | 33.33 | The release is deployed and critical production journeys pass. |  |  | 1 | Release Manager |  |  | 1 | 45 | M02-A08-S01 | No
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | Both | M02-A08-S03 | M02-A08 | Complete hypercare and release closure | Standard | Bulk Product Update (Push to POS Agent) | 2 | 50 | 10 | 33.34 | Priority production issues are resolved and the owner accepts operational handover. |  |  | 1 | Release Manager |  |  | 1 | 46 | M02-A08-S02 | No

## Template Index
Included Hybrid SDLC / Agile Templates
Template Name | Project Type | Entity | Brand | Project Name | Milestones | Import Rows
TGI - CBTL - DIWA - Hybrid SDLC Agile | Full Service Group: Customer Brand | TGI | CBTL | DIWA | 2 | 46

## Instructions
Hybrid SDLC / Agile Activity Template Instructions
Purpose | Recommended starting structures for the listed application projects. Review owners, durations, dependencies, weights, and acceptance criteria before importing.
Import | Open Activity Templates, choose Import, and upload this XLSX. The application groups rows by Template Name, Project Type, and Store Class.
Project Name | DAVID, LINK HUB, DIWA, and LINK PORTAL remain plain-text Project Name values; there is no Solution dropdown.
Hierarchy | Milestone = business capability or release; Activity = SDLC phase, sprint, or store rollout; Sub-Task = assignable accepted deliverable.
All Departments | All Departments' Process Implementation in LINK HUB contains one Activity per business process. Its Sub-Tasks cover department readiness plus the hybrid SDLC / Agile work needed to implement, test, release, and adopt that process in LINK HUB.
Collaboration Matrix | Use the matrix as the cross-department reporting view. Milestone marks the primary owning department and Waiting is the recommended initial state; replace these with current status or target week as planning progresses. Imported Sub-Tasks remain the source of progress percentages.
Task Board | Keep detailed user stories, bugs, and developer tasks on the Task Board. The Gantt should track accepted sprint/release outcomes.
Weights | Milestones total 100% per template, activities total 100% per milestone, and sub-tasks total 100% per activity.
Per Store | A Per Store activity is cloned after target stores are selected. Do not manually create 35 placeholder store rows.
NONOS DIWA | 35 is the recommended target-store count. The workbook does not create store assignments.
CBTL DIWA | Target-store count remains to be confirmed.
Safety | Import into a test environment first. Re-importing an identical template is skipped rather than overwriting it.

## WBS Guide
Work-Breakdown Guide
Level | Use | Example | Progress rule
Project | One application in one entity/brand context | DAVID · TGI · CBTL | Weighted milestone roll-up
Milestone | Business capability, release, or rollout outcome | Inventory Scanning with Barcode Scanner | Weighted activity roll-up
Activity | SDLC phase, Agile sprint, or per-store deployment | Sprint 1 – Core Workflow | Weighted sub-task roll-up
Sub-Task | Concrete deliverable with acceptance criteria | Product owner accepts sprint demo | Owner updates 0–100%
Task Board | Stories, bugs, coding tasks, and daily execution | API validation bug | Feeds its linked Gantt deliverable

## Lists (hidden)
Project Types | Entity Codes | Brand Codes | Store Classes | Activity Modes | Yes / No
Full Service Group: Customer Brand | TGI | NONOS | Regular | Standard | No
Corporate Group: Servicing Brand | GSI | CBTL | Kitchen | Per Store | Yes
| NCF | DSY | Both
DBS