## Import
Code | Parent Code | Name | Lead Time (Days) | Depends On Code | Run Parallel | Responsible Email | Acceptance Criteria | Remarks
DU-001 |  | Confirm stakeholder and decision-maker list | 2 |  | No |  | Required participants, approvers, and escalation contacts are identified. | Owner role: Project Manager. Deliverable: Approved stakeholder register. Include cashier, barista, store manager, web admin, support, and sponsor.
DU-002 | DU-001 | Select cashier and barista representatives | 1 |  | No |  | At least one representative for each operational role is confirmed. | Owner role: Operations Lead. Deliverable: Named store-level UAT participants
DU-003 | DU-001 | Select store manager and head-office admin representatives | 1 | DU-002 | Yes |  | Authorized representatives are confirmed. | Owner role: Operations Lead. Deliverable: Named management and admin participants
DU-004 |  | Prepare stable demo and UAT environment | 3 | DU-001 | No |  | Mobile and web admin applications are reachable and use the intended test environment. | Owner role: Technical Lead. Deliverable: Validated UAT environment. Development is complete; this is readiness validation, not feature development.
DU-005 | DU-004 | Create role-based test accounts | 1 |  | No |  | Accounts exist for cashier, barista, store manager, admin, and support roles. | Owner role: System Administrator. Deliverable: Test account register. Never include passwords in the import file.
DU-006 | DU-004 | Load realistic non-sensitive sample data | 1 | DU-005 | Yes |  | Stores, products, users, and transactions support all planned scenarios. | Owner role: System Administrator. Deliverable: UAT sample dataset
DU-007 | DU-004 | Verify role permissions and store access boundaries | 1 | DU-005 | No |  | Each role can access only approved functions and stores. | Owner role: QA Lead. Deliverable: Permission test evidence
DU-008 |  | Prepare end-to-end demo script | 2 | DU-006 | No |  | Script covers mobile activity, backend processing, admin review, and store-facing results. | Owner role: Business Analyst. Deliverable: Approved demo script
DU-009 | DU-008 | Prepare cashier and barista scenarios | 1 |  | No |  | Normal, correction, exception, and connectivity scenarios are documented. | Owner role: Business Analyst. Deliverable: Store-user scenario set
DU-010 | DU-008 | Prepare store manager and web admin scenarios | 1 | DU-009 | Yes |  | Administration, reporting, permissions, and exception workflows are documented. | Owner role: Business Analyst. Deliverable: Manager/admin scenario set
DU-011 |  | Conduct internal smoke test | 2 | DU-007 | No |  | No unresolved blocker prevents the stakeholder demo or UAT. | Owner role: QA Lead. Deliverable: Smoke-test report. Multiple predecessors are comma-separated.
DU-012 |  | Conduct stakeholder demonstration | 1 | DU-011 | No |  | End-to-end workflows are demonstrated and questions/actions are recorded. | Owner role: Product Owner. Deliverable: Demo attendance and meeting minutes
DU-013 | DU-012 | Classify demo feedback | 1 |  | No |  | Every item is classified as defect, pilot requirement, rollout requirement, future enhancement, or training item. | Owner role: Business Analyst. Deliverable: Prioritized feedback register
DU-014 |  | Execute facilitated user acceptance testing | 5 | DU-013 | No |  | Actual users execute all mandatory scenarios and results are recorded. | Owner role: QA Lead. Deliverable: Completed UAT evidence
DU-015 | DU-014 | Run cashier and barista UAT | 3 |  | No |  | All mandatory store-level scenarios pass or have accepted disposition. | Owner role: QA Lead. Deliverable: Store-user UAT results
DU-016 | DU-014 | Run store manager and web admin UAT | 3 | DU-015 | Yes |  | All mandatory management/admin scenarios pass or have accepted disposition. | Owner role: QA Lead. Deliverable: Admin UAT results

## Instructions
Gantt Milestone Import
Where | Project → Gantt tab → a milestone header → Import. Rows go into THAT milestone only.
Milestone | This copy was downloaded for: Stakeholder Demo and User Acceptance
Sheet | Only the "Import" sheet is read. Row 1 must keep the column names.
Order | Rows keep their order in the file. List each activity before its sub-tasks.
Dates | No dates are typed. The Gantt computes them from the project Day 1 Date, Lead Time, Depends On and Run Parallel.
Updating | Same name in the same place = update. Rows not in the file are left alone; nothing is deleted.
Safety | If any row has an error, nothing is imported and every error is listed.
Column | Rule
Code * | Any unique short code for this row, e.g. A-01. Used only to link rows inside this file.
Parent Code | Blank for an activity. For a sub-task, the Code of its activity (sub-tasks cannot have sub-tasks).
Name * | Activity or sub-task name. Re-importing the same name updates that row instead of adding a copy.
Lead Time (Days) * | Whole number, 1 or more. Counts the start day. An activity with sub-tasks uses the sum of its sub-tasks instead.
Depends On Code | Code of ONE row in this file it waits for. Blank = follows the row above it.
Run Parallel | Yes = starts the same day as its dependency. No (default) = starts the working day after it finishes.
Responsible Email | Email of an existing user to assign. Blank leaves the row unassigned (or keeps the current assignee on update).
Acceptance Criteria | Optional. What must be true to mark the row complete.
Remarks | Optional. Saved as the row's comments.