## README
LinkPortal Milestone Activity Import Template
Purpose | Import activities and subtasks directly into existing Gantt-chart milestones.
Primary import sheet | Activities_Import
Routing key | Milestone_Code identifies the destination milestone. Activity_Code is unique within that milestone.
Hierarchy | Import parent rows before child rows. Parent_Activity_Code is blank for top-level activities and points to Activity_Code for subtasks.
Dates | Start_Offset_Workdays and Duration_Workdays are relative to the destination milestone start date, avoiding hard-coded calendar dates.
Dependencies | Predecessor_Activity_Codes contains one or more same-milestone activity codes separated by commas. Dependency_Type is FS or SS.
Recommended import order | 1) Validate headers and milestone codes; 2) upsert top-level rows; 3) upsert subtasks; 4) resolve dependencies; 5) recalculate Gantt dates.
Recommended unique key | Milestone_Code + Activity_Code
Safe initial behavior | Validate the entire file first and reject the transaction if any required key, parent, predecessor, or lookup value is invalid.
Editing guidance | Edit the blue data cells in Activities_Import. Keep codes stable after the first import. Do not put passwords or secrets in this workbook.
Template contents | Four milestone groups covering stakeholder demo/UAT, pilot readiness, controlled pilot, and phased nationwide rollout.

## Milestones
Milestone_Code | Milestone_Name | Sequence | Objective | Suggested_Owner_Role | Initial_Status | Completion_Criteria
MS-DEMO-UAT | Stakeholder Demo and User Acceptance | 1 | Validate the completed mobile app and web admin panel with store and head-office users. | Business/Product Owner | Not Started | UAT sign-off granted with no unresolved blocker or critical defect.
MS-PILOT-READY | Pilot Readiness and Training | 2 | Prepare selected stores, users, data, training, support, and production controls for pilot launch. | Project Manager / Operations | Not Started | Formal pilot go/no-go approval granted.
MS-PILOT-RUN | Controlled Store Pilot and Evaluation | 3 | Operate the solution in selected stores, measure results, resolve issues, and obtain rollout approval. | Operations Lead | Not Started | Pilot accepted and nationwide rollout decision documented.
MS-ROLLOUT | Phased Nationwide Go-Live | 4 | Deploy the solution to approved stores in controlled waves and transfer it to business-as-usual support. | Deployment Lead | Not Started | All planned stores are live, stable, supported, and formally handed over.

## Activities_Import
Row_Action | Milestone_Code | Activity_Code | Parent_Activity_Code | WBS_Level | Activity_Name | Activity_Type | Description | Sequence | Start_Offset_Workdays | Duration_Workdays | Predecessor_Activity_Codes | Dependency_Type | Owner_Role | Participants | Deliverable | Acceptance_Criteria | Priority | Status | Mandatory | Notes
UPSERT | MS-DEMO-UAT | DU-001 |  | 1 | Confirm stakeholder and decision-maker list | Activity | Top-level work package for confirm stakeholder and decision-maker list. | 10 | 0 | 2 |  | FS | Project Manager | Product Owner; Operations; IT; Store Representatives | Approved stakeholder register | Required participants, approvers, and escalation contacts are identified. | High | Not Started | Yes | Include cashier, barista, store manager, web admin, support, and sponsor.
UPSERT | MS-DEMO-UAT | DU-002 | DU-001 | 2 | Select cashier and barista representatives | Subtask | Child task supporting select cashier and barista representatives. | 20 | 0 | 1 | DU-001 | SS | Operations Lead | Store Managers | Named store-level UAT participants | At least one representative for each operational role is confirmed. | High | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-003 | DU-001 | 2 | Select store manager and head-office admin representatives | Subtask | Child task supporting select store manager and head-office admin representatives. | 30 | 0 | 1 | DU-001 | SS | Operations Lead | Store Managers; Head Office | Named management and admin participants | Authorized representatives are confirmed. | High | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-004 |  | 1 | Prepare stable demo and UAT environment | Activity | Top-level work package for prepare stable demo and uat environment. | 40 | 1 | 3 | DU-001 | FS | Technical Lead | Backend; Frontend; Infrastructure | Validated UAT environment | Mobile and web admin applications are reachable and use the intended test environment. | Critical | Not Started | Yes | Development is complete; this is readiness validation, not feature development.
UPSERT | MS-DEMO-UAT | DU-005 | DU-004 | 2 | Create role-based test accounts | Subtask | Child task supporting create role-based test accounts. | 50 | 1 | 1 | DU-004 | SS | System Administrator | Technical Lead | Test account register | Accounts exist for cashier, barista, store manager, admin, and support roles. | Critical | Not Started | Yes | Never include passwords in the import file.
UPSERT | MS-DEMO-UAT | DU-006 | DU-004 | 2 | Load realistic non-sensitive sample data | Subtask | Child task supporting load realistic non-sensitive sample data. | 60 | 1 | 1 | DU-004 | SS | System Administrator | Business Analyst | UAT sample dataset | Stores, products, users, and transactions support all planned scenarios. | High | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-007 | DU-004 | 2 | Verify role permissions and store access boundaries | Subtask | Child task supporting verify role permissions and store access boundaries. | 70 | 2 | 1 | DU-005 | FS | QA Lead | Security; Business Analyst | Permission test evidence | Each role can access only approved functions and stores. | Critical | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-008 |  | 1 | Prepare end-to-end demo script | Activity | Top-level work package for prepare end-to-end demo script. | 80 | 2 | 2 | DU-006 | FS | Business Analyst | Product Owner; QA | Approved demo script | Script covers mobile activity, backend processing, admin review, and store-facing results. | High | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-009 | DU-008 | 2 | Prepare cashier and barista scenarios | Subtask | Child task supporting prepare cashier and barista scenarios. | 90 | 2 | 1 | DU-008 | SS | Business Analyst | Cashier; Barista | Store-user scenario set | Normal, correction, exception, and connectivity scenarios are documented. | High | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-010 | DU-008 | 2 | Prepare store manager and web admin scenarios | Subtask | Child task supporting prepare store manager and web admin scenarios. | 100 | 2 | 1 | DU-008 | SS | Business Analyst | Store Manager; Web Admin | Manager/admin scenario set | Administration, reporting, permissions, and exception workflows are documented. | High | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-011 |  | 1 | Conduct internal smoke test | Activity | Top-level work package for conduct internal smoke test. | 110 | 4 | 2 | DU-007,DU-009,DU-010 | FS | QA Lead | Technical Team | Smoke-test report | No unresolved blocker prevents the stakeholder demo or UAT. | Critical | Not Started | Yes | Multiple predecessors are comma-separated.
UPSERT | MS-DEMO-UAT | DU-012 |  | 1 | Conduct stakeholder demonstration | Activity | Top-level work package for conduct stakeholder demonstration. | 120 | 6 | 1 | DU-011 | FS | Product Owner | All Stakeholders | Demo attendance and meeting minutes | End-to-end workflows are demonstrated and questions/actions are recorded. | Critical | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-013 | DU-012 | 2 | Classify demo feedback | Subtask | Child task supporting classify demo feedback. | 130 | 7 | 1 | DU-012 | FS | Business Analyst | Product Owner; QA; Technical Lead | Prioritized feedback register | Every item is classified as defect, pilot requirement, rollout requirement, future enhancement, or training item. | High | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-014 |  | 1 | Execute facilitated user acceptance testing | Activity | Top-level work package for execute facilitated user acceptance testing. | 140 | 8 | 5 | DU-013 | FS | QA Lead | Cashier; Barista; Store Manager; Web Admin | Completed UAT evidence | Actual users execute all mandatory scenarios and results are recorded. | Critical | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-015 | DU-014 | 2 | Run cashier and barista UAT | Subtask | Child task supporting run cashier and barista uat. | 150 | 8 | 3 | DU-014 | SS | QA Lead | Cashier; Barista | Store-user UAT results | All mandatory store-level scenarios pass or have accepted disposition. | Critical | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-016 | DU-014 | 2 | Run store manager and web admin UAT | Subtask | Child task supporting run store manager and web admin uat. | 160 | 8 | 3 | DU-014 | SS | QA Lead | Store Manager; Web Admin | Admin UAT results | All mandatory management/admin scenarios pass or have accepted disposition. | Critical | Not Started | Yes
UPSERT | MS-DEMO-UAT | DU-017 |  | 1 | Resolve and retest pilot-blocking defects | Activity | Top-level work package for resolve and retest pilot-blocking defects. | 170 | 13 | 5 | DU-015,DU-016 | FS | Technical Lead | QA; Product Owner | Defect closure evidence | All critical/high pilot-blocking defects are closed and regression-tested. | Critical | Not Started | Yes | Duration is an initial planning estimate and can be updated.
UPSERT | MS-DEMO-UAT | DU-018 |  | 1 | Obtain formal UAT sign-off | Activity | Top-level work package for obtain formal uat sign-off. | 180 | 18 | 1 | DU-017 | FS | Business/Product Owner | Operations; IT | Signed UAT approval | Business owner approves progression to pilot readiness. | Critical | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-001 |  | 1 | Select and approve pilot stores | Activity | Top-level work package for select and approve pilot stores. | 10 | 0 | 2 |  | FS | Operations Lead | Product Owner; Regional Managers | Approved pilot-store list | Pilot stores represent suitable volume, region, and connectivity conditions. | Critical | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-002 |  | 1 | Define pilot scope, dates, and success measures | Activity | Top-level work package for define pilot scope, dates, and success measures. | 20 | 0 | 2 | PR-001 | SS | Project Manager | Product Owner; Operations; IT | Pilot charter | Pilot period, included workflows, KPIs, decision rules, and escalation paths are approved. | Critical | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-003 |  | 1 | Prepare user training materials | Activity | Top-level work package for prepare user training materials. | 30 | 1 | 4 | PR-002 | SS | Training Lead | Business Analyst; Store Champions | Role-based training package | Quick guides, admin guide, FAQs, and support instructions are approved. | High | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-004 | PR-003 | 2 | Prepare cashier and barista quick guide | Subtask | Child task supporting prepare cashier and barista quick guide. | 40 | 1 | 2 | PR-003 | SS | Training Lead | Store Representatives | Store-user quick guide | Guide covers daily workflow, exceptions, login, and support escalation. | High | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-005 | PR-003 | 2 | Prepare store manager and web admin guide | Subtask | Child task supporting prepare store manager and web admin guide. | 50 | 1 | 3 | PR-003 | SS | Training Lead | Store Manager; Web Admin | Manager/admin guide | Guide covers administration, monitoring, reporting, and exceptions. | High | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-006 |  | 1 | Establish pilot support and escalation model | Activity | Top-level work package for establish pilot support and escalation model. | 60 | 2 | 3 | PR-002 | FS | Support Lead | Operations; Technical Team | Support matrix and service targets | Level 1, Level 2, development escalation, hours, and response targets are documented. | Critical | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-007 |  | 1 | Configure pilot production data and users | Activity | Top-level work package for configure pilot production data and users. | 70 | 4 | 3 | PR-001 | FS | System Administrator | Store Managers; Technical Lead | Validated pilot configuration | Stores, roles, users, and required master data are complete and accurate. | Critical | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-008 | PR-007 | 2 | Verify pilot devices, browsers, and connectivity | Subtask | Child task supporting verify pilot devices, browsers, and connectivity. | 80 | 4 | 2 | PR-007 | SS | IT Support | Store Champions | Technical readiness checklist | Every pilot store meets supported device, browser, and network requirements. | Critical | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-009 |  | 1 | Train pilot users and store champions | Activity | Top-level work package for train pilot users and store champions. | 90 | 6 | 4 | PR-003,PR-007 | FS | Training Lead | Pilot Users; Support | Training attendance and readiness results | Required users complete training and nominated champions pass readiness checks. | Critical | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-010 |  | 1 | Validate monitoring, backup, and recovery readiness | Activity | Top-level work package for validate monitoring, backup, and recovery readiness. | 100 | 7 | 2 | PR-006,PR-007 | FS | Technical Lead | Infrastructure; Support | Operational readiness evidence | Monitoring and recovery procedures are tested and owned. | Critical | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-011 |  | 1 | Document pilot rollback and business-continuity procedure | Activity | Top-level work package for document pilot rollback and business-continuity procedure. | 110 | 7 | 2 | PR-006 | FS | Project Manager | Operations; IT | Approved rollback plan | Stores can continue operating safely if the pilot must be suspended. | Critical | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-012 |  | 1 | Run production-readiness smoke test | Activity | Top-level work package for run production-readiness smoke test. | 120 | 10 | 2 | PR-008,PR-009,PR-010,PR-011 | FS | QA Lead | Pilot Team | Readiness test report | All critical pilot workflows pass in the production configuration. | Critical | Not Started | Yes
UPSERT | MS-PILOT-READY | PR-013 |  | 1 | Conduct pilot go/no-go review | Activity | Top-level work package for conduct pilot go/no-go review. | 130 | 12 | 1 | PR-012 | FS | Project Sponsor | Product Owner; Operations; IT | Documented go/no-go decision | Authorized stakeholders approve pilot activation or record blocking actions. | Critical | Not Started | Yes
UPSERT | MS-PILOT-RUN | PI-001 |  | 1 | Activate solution in pilot stores | Activity | Top-level work package for activate solution in pilot stores. | 10 | 0 | 1 |  | FS | Deployment Lead | IT Support; Store Champions | Pilot activation record | All approved pilot stores are activated according to the go-live checklist. | Critical | Not Started | Yes | Requires prior milestone MS-PILOT-READY completion.
UPSERT | MS-PILOT-RUN | PI-002 |  | 1 | Perform opening-day checks | Activity | Top-level work package for perform opening-day checks. | 20 | 0 | 1 | PI-001 | SS | Support Lead | Store Champions; QA | Day-one verification log | Users can log in and end-to-end transactions are visible in the web admin panel. | Critical | Not Started | Yes
UPSERT | MS-PILOT-RUN | PI-003 |  | 1 | Monitor system health and application errors | Activity | Top-level work package for monitor system health and application errors. | 30 | 0 | 15 | PI-001 | SS | Technical Lead | Support; Infrastructure | Pilot monitoring log | Availability, errors, and performance are reviewed throughout the pilot. | Critical | Not Started | Yes | Ongoing activity for the full pilot period.
UPSERT | MS-PILOT-RUN | PI-004 |  | 1 | Reconcile pilot transactions and data | Activity | Top-level work package for reconcile pilot transactions and data. | 40 | 1 | 14 | PI-002 | FS | Operations Lead | Finance; Store Managers; Web Admin | Daily reconciliation records | Pilot data is complete, accurate, and explainable. | Critical | Not Started | Yes
UPSERT | MS-PILOT-RUN | PI-005 |  | 1 | Operate pilot incident and support process | Activity | Top-level work package for operate pilot incident and support process. | 50 | 0 | 15 | PI-001 | SS | Support Lead | Technical Team; Operations | Incident register | Incidents have severity, owner, response, resolution, and closure evidence. | Critical | Not Started | Yes
UPSERT | MS-PILOT-RUN | PI-006 |  | 1 | Conduct regular pilot check-ins | Activity | Top-level work package for conduct regular pilot check-ins. | 60 | 2 | 12 | PI-002 | FS | Project Manager | Pilot Stakeholders | Check-in minutes and action log | Operational issues and actions are reviewed on the agreed cadence. | High | Not Started | Yes
UPSERT | MS-PILOT-RUN | PI-007 |  | 1 | Collect structured user feedback | Activity | Top-level work package for collect structured user feedback. | 70 | 5 | 8 | PI-002 | FS | Business Analyst | Cashier; Barista; Store Manager; Web Admin | User feedback summary | Feedback is collected from every pilot user group. | High | Not Started | Yes
UPSERT | MS-PILOT-RUN | PI-008 |  | 1 | Resolve critical pilot issues and verify fixes | Activity | Top-level work package for resolve critical pilot issues and verify fixes. | 80 | 1 | 14 | PI-005 | SS | Technical Lead | QA; Product Owner | Verified issue resolutions | No unresolved critical production issue remains at pilot completion. | Critical | Not Started | Yes
UPSERT | MS-PILOT-RUN | PI-009 |  | 1 | Evaluate pilot against success criteria | Activity | Top-level work package for evaluate pilot against success criteria. | 90 | 15 | 3 | PI-003,PI-004,PI-005,PI-007,PI-008 | FS | Project Manager | Product Owner; Operations; IT | Pilot evaluation report | Results cover adoption, availability, data accuracy, incidents, support, and user satisfaction. | Critical | Not Started | Yes
UPSERT | MS-PILOT-RUN | PI-010 |  | 1 | Conduct nationwide rollout decision meeting | Activity | Top-level work package for conduct nationwide rollout decision meeting. | 100 | 18 | 1 | PI-009 | FS | Project Sponsor | Business; Operations; IT | Approved rollout decision | Decision is recorded as go, conditional go, extended pilot, or no-go. | Critical | Not Started | Yes
UPSERT | MS-ROLLOUT | RO-001 |  | 1 | Define rollout waves and store sequence | Activity | Top-level work package for define rollout waves and store sequence. | 10 | 0 | 3 |  | FS | Deployment Lead | Operations; Regional Managers; IT | Approved rollout-wave plan | Every approved store belongs to a wave with owner and target window. | Critical | Not Started | Yes | Requires prior milestone MS-PILOT-RUN approval.
UPSERT | MS-ROLLOUT | RO-002 |  | 1 | Prepare reusable store onboarding checklist | Activity | Top-level work package for prepare reusable store onboarding checklist. | 20 | 0 | 2 | RO-001 | SS | Project Manager | Operations; Support | Store onboarding checklist | Checklist covers data, users, devices, training, communications, support, and acceptance. | High | Not Started | Yes
UPSERT | MS-ROLLOUT | RO-003 |  | 1 | Prepare stores for rollout wave | Activity | Top-level work package for prepare stores for rollout wave. | 30 | 3 | 5 | RO-001,RO-002 | FS | Regional Deployment Lead | Store Managers; IT Support | Wave readiness pack | All stores in the wave pass data, account, device, connectivity, and training checks. | Critical | Not Started | Yes | Repeat once per wave or duplicate rows during import.
UPSERT | MS-ROLLOUT | RO-004 | RO-003 | 2 | Validate store master data and user accounts | Subtask | Child task supporting validate store master data and user accounts. | 40 | 3 | 2 | RO-003 | SS | System Administrator | Store Managers | Validated store configuration | Store assignments, roles, users, and master data are correct. | Critical | Not Started | Yes
UPSERT | MS-ROLLOUT | RO-005 | RO-003 | 2 | Complete wave user training | Subtask | Child task supporting complete wave user training. | 50 | 3 | 3 | RO-003 | SS | Training Lead | Store Users; Champions | Training completion record | Required users complete training before activation. | Critical | Not Started | Yes
UPSERT | MS-ROLLOUT | RO-006 | RO-003 | 2 | Send store go-live communications | Subtask | Child task supporting send store go-live communications. | 60 | 5 | 1 | RO-004,RO-005 | FS | Communications Lead | Store Teams; Support | Go-live notice | Users receive timing, responsibilities, support, and fallback instructions. | High | Not Started | Yes
UPSERT | MS-ROLLOUT | RO-007 |  | 1 | Activate rollout wave | Activity | Top-level work package for activate rollout wave. | 70 | 8 | 1 | RO-003 | FS | Deployment Lead | IT Support; Store Champions | Wave activation record | All approved stores in the wave are activated using the checklist. | Critical | Not Started | Yes
UPSERT | MS-ROLLOUT | RO-008 |  | 1 | Provide opening-day and wave hypercare support | Activity | Top-level work package for provide opening-day and wave hypercare support. | 80 | 8 | 5 | RO-007 | SS | Support Lead | Technical Team; Operations | Hypercare log | Issues are monitored, prioritized, resolved, and communicated during the wave. | Critical | Not Started | Yes
UPSERT | MS-ROLLOUT | RO-009 |  | 1 | Reconcile and accept rollout wave | Activity | Top-level work package for reconcile and accept rollout wave. | 90 | 9 | 4 | RO-007 | FS | Operations Lead | Store Managers; Finance; Web Admin | Wave acceptance record | Data reconciles and each store is accepted or has an approved action plan. | Critical | Not Started | Yes
UPSERT | MS-ROLLOUT | RO-010 |  | 1 | Review lessons before next wave | Activity | Top-level work package for review lessons before next wave. | 100 | 13 | 1 | RO-008,RO-009 | FS | Project Manager | Deployment Team | Wave retrospective actions | Lessons and required corrections are applied before the next wave. | High | Not Started | Yes | Repeat RO-003 through RO-010 for each rollout wave.
UPSERT | MS-ROLLOUT | RO-011 |  | 1 | Transition to business-as-usual support | Activity | Top-level work package for transition to business-as-usual support. | 110 | 14 | 5 | RO-010 | FS | Support Lead | Operations; Technical Team | Support handover pack | Application support, user administration, onboarding, monitoring, and release ownership are accepted. | Critical | Not Started | Yes | Schedule after final rollout wave.
UPSERT | MS-ROLLOUT | RO-012 |  | 1 | Close rollout milestone | Activity | Top-level work package for close rollout milestone. | 120 | 19 | 1 | RO-011 | FS | Business/Product Owner | Project Sponsor; Operations; IT | Final acceptance and closure report | All planned stores are stable and formal operational acceptance is signed. | Critical | Not Started | Yes

## Field_Definitions
Column_Name | Required | Data_Type / Format | Allowed Values / Rule | Definition
Row_Action | Yes | Text | UPSERT | Importer behavior for the row. Use UPSERT to create or update by Milestone_Code + Activity_Code.
Milestone_Code | Yes | Text | Must exist in the app or in the Milestones sheet if milestone creation is later supported. | Stable external key of the destination milestone. If importing from inside one selected milestone, the app may validate or ignore this value.
Activity_Code | Yes | Text | Unique within Milestone_Code; recommended pattern AA-999. | Stable activity key unique within the milestone.
Parent_Activity_Code | No | Text | Blank or an Activity_Code in the same milestone. | Activity_Code of the parent activity in the same milestone. Blank means a top-level activity.
WBS_Level | Yes | Integer | 1 or 2 | Hierarchy level: 1 for activity, 2 for subtask.
Activity_Name | Yes | Text | Free text | User-facing activity or subtask title.
Activity_Type | Yes | Text | Activity; Subtask | Activity or Subtask.
Description | No | Text | Free text | Purpose or scope of the activity.
Sequence | Yes | Integer | Positive integer | Sort order within the milestone; increments of 10 allow later insertions.
Start_Offset_Workdays | No | Integer | Integer >= 0 | Suggested start offset from the milestone start date, in working days.
Duration_Workdays | Yes | Integer | Integer >= 1 | Suggested planned duration in working days.
Predecessor_Activity_Codes | No | Text | Blank or comma-separated same-milestone Activity_Code values. | Comma-separated Activity_Code values in the same milestone. Blank means none.
Dependency_Type | No | Text | FS; SS | FS = Finish-to-Start; SS = Start-to-Start.
Owner_Role | Yes | Text | Free text | Accountable role; map to a real user/team during scheduling.
Participants | No | Text | Free text | Semicolon-separated participating roles.
Deliverable | No | Text | Free text | Expected tangible output.
Acceptance_Criteria | Yes | Text | Free text | Condition required to mark the row complete.
Priority | Yes | Text | Critical; High; Medium; Low | Critical, High, Medium, or Low.
Status | Yes | Text | Not Started; Scheduled; In Progress; Blocked; Ready for Review; Completed; Deferred | Initial workflow status.
Mandatory | Yes | Text | Yes; No | Yes or No.
Notes | No | Text | Free text | Implementation or scheduling guidance; not part of acceptance criteria.

## Lookup_Values
Row_Action | Activity_Type | Dependency_Type | Priority | Status | Mandatory
UPSERT | Activity | FS | Critical | Not Started | Yes
| Subtask | SS | High | Scheduled | No
|  |  | Medium | In Progress
|  |  | Low | Blocked
Ready for Review
Completed
Deferred