## Business Requirements
Business Requirement Document
Objective | Correct Milestone Schedule Computation
Current Issue | System computes Finish = Start + Lead Time instead of Finish = Start + Lead Time - 1, causing an off-by-one error.
Business Rules
Rule | Formula | Example
Milestone Lead Time | sum | 2+2+4+2 = 10 days
Milestone Start | Previous Finish + 1 | 10 + 1 = Day 11
Milestone Finish | Finish = Start + Lead Time - 1 | 1 + 10 - 1 = Day 10
Sub-task Start | Previous Sub-task Finish + 1 | 2 -> Day 3
Sub-task Finish | Start + Lead Time - 1 | 3 + 2 - 1 = Day 4
Comparison Example
Milestone | Lead Time | Goal | Current System | Expected Formula
Site Identification & Assessment | 10 | Day 1 - Day 10 | Day 1 - Day 11 | 1 + 10 - 1 = 10
Management Review & Endorsement | 5 | Day 11 - Day 15 | Day 12 - Day 19 | 11 + 5 - 1 = 15
Site Validation & Commercial Negotiation | 10 | Day 16 - Day 25 | Day 20 - Day 30 | 16 + 10 - 1 = 25
Worked Scheduling Example
Sub-task | Lead Time | Start | Finish | Formula
Document Review | 2 | 1 | 2 | Start + LT - 1
Update Proposal | 2 | 3 | 4 | Start + LT - 1
Secure Offer Sheet | 4 | 5 | 8 | Start + LT - 1
Additional Activity | 2 | 9 | 10 | Start + LT - 1
Milestone Total |  |  | 10
Milestone Lead Time | 10
Acceptance Criteria
Scenario | Expected Result
Start = 1, Lead Time = 10 | Finish=10
Previous Finish = 10 | Next Start=11
Lead Time changed 4->6 | Recalculate downstream milestones automatically
Reference
Existing |  |  |  |  | Goal

## Developer Logic
6
Step | Logic
1 | If Dependency is blank, Start = Day 1
2 | Else If Can Run Parallel = No, Start = Dependency Finish + 1
3 | Else If Can Run Parallel = Yes, Start = Dependency Start
4 | Finish = Start + Lead Time - 1
5 | Parent Milestone Lead Time = Sum of Child Lead Times
6 | Parent Finish = Latest Child Finish
7 | Recalculate all downstream milestones whenever Lead Time, Dependency, or Parallel flag changes

## Data Dictionary
Field | Type | Editable | Business Rule
Lead Time | Integer | Yes | Must be >0
Start Day | Integer | No | Calculated
Finish Day | Integer | No | Calculated
Dependency | Lookup | Yes | Cannot reference itself
Can Run Parallel | Boolean | Yes | Yes=Start with dependency, No=Start after dependency finish
Milestone Lead Time | Integer | No | Sum of child Lead Times

## UAT Test Cases
Test Case | Input | Expected Result
TC-001 | Start=1, LT=10 | Finish=10
TC-002 | Previous Finish=10 | Next Start=11
TC-003 | Parallel=Yes | Dependent activity starts same day as dependency
TC-004 | Change LT 4→6 | All downstream milestones recalculated
TC-005 | Insert new sub-task | Parent milestone lead time updates
TC-006 | Delete sub-task | Parent finish recalculated