## Activity Templates
Template Name | Project Type | Entity Code | Brand Code | Project Name | Store Class | Row Key | Parent Row Key | Activity | Activity Mode | Milestone | Milestone Order | Milestone Weight % | Activity Weight % | Sub-Task Weight % | Acceptance Criteria | Asset Item | Model Specs | Quantity | Responsible | Department | Sub Unit | Duration Days | Order | Requisite Row Key | Can Run Parallel
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01 |  | New Store Opening | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | New Store Opening is completed and accepted. |  |  | 1 | Lead: Pam ¦ Partner: Daphne | Business Development |  | 18 | 1 |  | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S01 | M01-A01 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Pam and Daphne confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for New Store Opening. |  |  | 1 | Lead: Pam ¦ Partner: Daphne | Business Development |  | 1 | 2 |  | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S02 | M01-A01 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for New Store Opening are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Business Development |  | 1 | 3 | M01-A01-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S03 | M01-A01 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the New Store Opening workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 4 | M01-A01-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S04 | M01-A01 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the New Store Opening workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 5 | M01-A01-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S05 | M01-A01 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the New Store Opening workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 6 | M01-A01-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S06 | M01-A01 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the New Store Opening workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 7 | M01-A01-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S07 | M01-A01 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the New Store Opening workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 8 | M01-A01-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S08 | M01-A01 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the New Store Opening workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 9 | M01-A01-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S09 | M01-A01 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the New Store Opening workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 10 | M01-A01-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S10 | M01-A01 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the New Store Opening workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 11 | M01-A01-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S11 | M01-A01 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the New Store Opening workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 12 | M01-A01-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S12 | M01-A01 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the New Store Opening workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 13 | M01-A01-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S13 | M01-A01 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the New Store Opening workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 14 | M01-A01-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S14 | M01-A01 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for New Store Opening are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 15 | M01-A01-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S15 | M01-A01 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for New Store Opening meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 16 | M01-A01-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S16 | M01-A01 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The New Store Opening release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 17 | M01-A01-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S17 | M01-A01 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative New Store Opening scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Pam ¦ Partner: Daphne / Key Users | Business Development |  | 1 | 18 | M01-A01-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A01-S18 | M01-A01 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The New Store Opening workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Business Development |  | 1 | 19 | M01-A01-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02 |  | Store Closure | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | Store Closure is completed and accepted. |  |  | 1 | Lead: Pam ¦ Partner: Daphne | Business Development |  | 18 | 20 | M01-A01 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S01 | M01-A02 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Pam and Daphne confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for Store Closure. |  |  | 1 | Lead: Pam ¦ Partner: Daphne | Business Development |  | 1 | 21 | M01-A01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S02 | M01-A02 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for Store Closure are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Business Development |  | 1 | 22 | M01-A02-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S03 | M01-A02 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Closure workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 23 | M01-A02-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S04 | M01-A02 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Closure workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 24 | M01-A02-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S05 | M01-A02 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Closure workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 25 | M01-A02-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S06 | M01-A02 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Closure workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 26 | M01-A02-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S07 | M01-A02 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Closure workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 27 | M01-A02-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S08 | M01-A02 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Closure workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 28 | M01-A02-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S09 | M01-A02 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Closure workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 29 | M01-A02-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S10 | M01-A02 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Closure workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 30 | M01-A02-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S11 | M01-A02 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Closure workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 31 | M01-A02-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S12 | M01-A02 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Closure workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 32 | M01-A02-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S13 | M01-A02 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Closure workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 33 | M01-A02-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S14 | M01-A02 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for Store Closure are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 34 | M01-A02-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S15 | M01-A02 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for Store Closure meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 35 | M01-A02-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S16 | M01-A02 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The Store Closure release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 36 | M01-A02-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S17 | M01-A02 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative Store Closure scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Pam ¦ Partner: Daphne / Key Users | Business Development |  | 1 | 37 | M01-A02-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A02-S18 | M01-A02 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The Store Closure workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Business Development |  | 1 | 38 | M01-A02-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03 |  | Store Renovation | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | Store Renovation is completed and accepted. |  |  | 1 | Lead: Pam ¦ Partner: Daphne | Project Development |  | 18 | 39 | M01-A02 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S01 | M01-A03 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Pam and Daphne confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for Store Renovation. |  |  | 1 | Lead: Pam ¦ Partner: Daphne | Project Development |  | 1 | 40 | M01-A02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S02 | M01-A03 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for Store Renovation are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Project Development |  | 1 | 41 | M01-A03-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S03 | M01-A03 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Renovation workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 42 | M01-A03-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S04 | M01-A03 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Renovation workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 43 | M01-A03-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S05 | M01-A03 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Renovation workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 44 | M01-A03-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S06 | M01-A03 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Renovation workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 45 | M01-A03-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S07 | M01-A03 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Renovation workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 46 | M01-A03-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S08 | M01-A03 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Renovation workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 47 | M01-A03-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S09 | M01-A03 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Renovation workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 48 | M01-A03-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S10 | M01-A03 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Renovation workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 49 | M01-A03-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S11 | M01-A03 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Renovation workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 50 | M01-A03-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S12 | M01-A03 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Renovation workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 51 | M01-A03-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S13 | M01-A03 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Store Renovation workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 52 | M01-A03-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S14 | M01-A03 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for Store Renovation are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 53 | M01-A03-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S15 | M01-A03 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for Store Renovation meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 54 | M01-A03-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S16 | M01-A03 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The Store Renovation release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 55 | M01-A03-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S17 | M01-A03 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative Store Renovation scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Pam ¦ Partner: Daphne / Key Users | Project Development |  | 1 | 56 | M01-A03-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A03-S18 | M01-A03 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The Store Renovation workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Project Development |  | 1 | 57 | M01-A03-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04 |  | Requisition Process | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | Requisition Process is completed and accepted. |  |  | 1 | Lead: Cel ¦ Partner: Brendan | Supply Chain Management |  | 18 | 58 | M01-A03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S01 | M01-A04 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Cel and Brendan confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for Requisition Process. |  |  | 1 | Lead: Cel ¦ Partner: Brendan | Supply Chain Management |  | 1 | 59 | M01-A03 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S02 | M01-A04 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for Requisition Process are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Supply Chain Management |  | 1 | 60 | M01-A04-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S03 | M01-A04 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Requisition Process workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 61 | M01-A04-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S04 | M01-A04 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Requisition Process workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 62 | M01-A04-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S05 | M01-A04 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Requisition Process workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 63 | M01-A04-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S06 | M01-A04 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Requisition Process workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 64 | M01-A04-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S07 | M01-A04 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Requisition Process workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 65 | M01-A04-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S08 | M01-A04 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Requisition Process workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 66 | M01-A04-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S09 | M01-A04 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Requisition Process workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 67 | M01-A04-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S10 | M01-A04 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Requisition Process workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 68 | M01-A04-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S11 | M01-A04 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Requisition Process workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 69 | M01-A04-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S12 | M01-A04 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Requisition Process workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 70 | M01-A04-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S13 | M01-A04 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Requisition Process workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 71 | M01-A04-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S14 | M01-A04 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for Requisition Process are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 72 | M01-A04-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S15 | M01-A04 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for Requisition Process meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 73 | M01-A04-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S16 | M01-A04 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The Requisition Process release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 74 | M01-A04-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S17 | M01-A04 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative Requisition Process scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Cel ¦ Partner: Brendan / Key Users | Supply Chain Management |  | 1 | 75 | M01-A04-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A04-S18 | M01-A04 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The Requisition Process workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Supply Chain Management |  | 1 | 76 | M01-A04-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05 |  | Purchasing Process | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | Purchasing Process is completed and accepted. |  |  | 1 | Lead: Cel ¦ Partner: Brendan | Supply Chain Management |  | 18 | 77 | M01-A04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S01 | M01-A05 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Cel and Brendan confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for Purchasing Process. |  |  | 1 | Lead: Cel ¦ Partner: Brendan | Supply Chain Management |  | 1 | 78 | M01-A04 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S02 | M01-A05 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for Purchasing Process are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Supply Chain Management |  | 1 | 79 | M01-A05-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S03 | M01-A05 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Purchasing Process workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 80 | M01-A05-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S04 | M01-A05 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Purchasing Process workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 81 | M01-A05-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S05 | M01-A05 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Purchasing Process workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 82 | M01-A05-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S06 | M01-A05 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Purchasing Process workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 83 | M01-A05-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S07 | M01-A05 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Purchasing Process workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 84 | M01-A05-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S08 | M01-A05 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Purchasing Process workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 85 | M01-A05-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S09 | M01-A05 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Purchasing Process workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 86 | M01-A05-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S10 | M01-A05 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Purchasing Process workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 87 | M01-A05-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S11 | M01-A05 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Purchasing Process workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 88 | M01-A05-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S12 | M01-A05 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Purchasing Process workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 89 | M01-A05-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S13 | M01-A05 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Purchasing Process workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 90 | M01-A05-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S14 | M01-A05 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for Purchasing Process are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 91 | M01-A05-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S15 | M01-A05 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for Purchasing Process meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 92 | M01-A05-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S16 | M01-A05 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The Purchasing Process release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 93 | M01-A05-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S17 | M01-A05 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative Purchasing Process scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Cel ¦ Partner: Brendan / Key Users | Supply Chain Management |  | 1 | 94 | M01-A05-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A05-S18 | M01-A05 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The Purchasing Process workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Supply Chain Management |  | 1 | 95 | M01-A05-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06 |  | Procure to Pay | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | Procure to Pay is completed and accepted. |  |  | 1 | Lead: Anna, Rach ¦ Partner: Becky | Finance and Accounting |  | 18 | 96 | M01-A05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S01 | M01-A06 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Anna, Rach and Becky confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for Procure to Pay. |  |  | 1 | Lead: Anna, Rach ¦ Partner: Becky | Finance and Accounting |  | 1 | 97 | M01-A05 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S02 | M01-A06 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for Procure to Pay are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Finance and Accounting |  | 1 | 98 | M01-A06-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S03 | M01-A06 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Procure to Pay workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 99 | M01-A06-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S04 | M01-A06 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Procure to Pay workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 100 | M01-A06-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S05 | M01-A06 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Procure to Pay workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 101 | M01-A06-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S06 | M01-A06 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Procure to Pay workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 102 | M01-A06-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S07 | M01-A06 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Procure to Pay workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 103 | M01-A06-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S08 | M01-A06 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Procure to Pay workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 104 | M01-A06-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S09 | M01-A06 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Procure to Pay workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 105 | M01-A06-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S10 | M01-A06 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Procure to Pay workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 106 | M01-A06-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S11 | M01-A06 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Procure to Pay workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 107 | M01-A06-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S12 | M01-A06 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Procure to Pay workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 108 | M01-A06-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S13 | M01-A06 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Procure to Pay workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 109 | M01-A06-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S14 | M01-A06 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for Procure to Pay are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 110 | M01-A06-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S15 | M01-A06 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for Procure to Pay meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 111 | M01-A06-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S16 | M01-A06 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The Procure to Pay release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 112 | M01-A06-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S17 | M01-A06 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative Procure to Pay scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Anna, Rach ¦ Partner: Becky / Key Users | Finance and Accounting |  | 1 | 113 | M01-A06-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A06-S18 | M01-A06 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The Procure to Pay workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Finance and Accounting |  | 1 | 114 | M01-A06-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07 |  | Campaign Launch | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | Campaign Launch is completed and accepted. |  |  | 1 | Lead: Kim, Josie ¦ Partner: Rach | Marketing |  | 18 | 115 | M01-A06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S01 | M01-A07 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Kim, Josie and Rach confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for Campaign Launch. |  |  | 1 | Lead: Kim, Josie ¦ Partner: Rach | Marketing |  | 1 | 116 | M01-A06 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S02 | M01-A07 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for Campaign Launch are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Marketing |  | 1 | 117 | M01-A07-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S03 | M01-A07 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Campaign Launch workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 118 | M01-A07-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S04 | M01-A07 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Campaign Launch workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 119 | M01-A07-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S05 | M01-A07 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Campaign Launch workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 120 | M01-A07-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S06 | M01-A07 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Campaign Launch workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 121 | M01-A07-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S07 | M01-A07 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Campaign Launch workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 122 | M01-A07-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S08 | M01-A07 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Campaign Launch workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 123 | M01-A07-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S09 | M01-A07 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Campaign Launch workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 124 | M01-A07-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S10 | M01-A07 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Campaign Launch workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 125 | M01-A07-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S11 | M01-A07 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Campaign Launch workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 126 | M01-A07-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S12 | M01-A07 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Campaign Launch workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 127 | M01-A07-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S13 | M01-A07 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Campaign Launch workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 128 | M01-A07-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S14 | M01-A07 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for Campaign Launch are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 129 | M01-A07-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S15 | M01-A07 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for Campaign Launch meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 130 | M01-A07-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S16 | M01-A07 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The Campaign Launch release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 131 | M01-A07-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S17 | M01-A07 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative Campaign Launch scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Kim, Josie ¦ Partner: Rach / Key Users | Marketing |  | 1 | 132 | M01-A07-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A07-S18 | M01-A07 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The Campaign Launch workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Marketing |  | 1 | 133 | M01-A07-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08 |  | Product Launch | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | Product Launch is completed and accepted. |  |  | 1 | Lead: Kim, Josie ¦ Partner: Cel | Marketing |  | 18 | 134 | M01-A07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S01 | M01-A08 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Kim, Josie and Cel confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for Product Launch. |  |  | 1 | Lead: Kim, Josie ¦ Partner: Cel | Marketing |  | 1 | 135 | M01-A07 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S02 | M01-A08 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for Product Launch are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Marketing |  | 1 | 136 | M01-A08-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S03 | M01-A08 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Product Launch workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 137 | M01-A08-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S04 | M01-A08 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Product Launch workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 138 | M01-A08-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S05 | M01-A08 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Product Launch workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 139 | M01-A08-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S06 | M01-A08 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Product Launch workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 140 | M01-A08-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S07 | M01-A08 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Product Launch workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 141 | M01-A08-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S08 | M01-A08 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Product Launch workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 142 | M01-A08-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S09 | M01-A08 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Product Launch workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 143 | M01-A08-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S10 | M01-A08 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Product Launch workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 144 | M01-A08-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S11 | M01-A08 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Product Launch workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 145 | M01-A08-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S12 | M01-A08 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Product Launch workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 146 | M01-A08-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S13 | M01-A08 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Product Launch workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 147 | M01-A08-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S14 | M01-A08 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for Product Launch are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 148 | M01-A08-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S15 | M01-A08 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for Product Launch meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 149 | M01-A08-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S16 | M01-A08 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The Product Launch release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 150 | M01-A08-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S17 | M01-A08 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative Product Launch scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Kim, Josie ¦ Partner: Cel / Key Users | Marketing |  | 1 | 151 | M01-A08-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A08-S18 | M01-A08 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The Product Launch workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Marketing |  | 1 | 152 | M01-A08-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09 |  | Project Development | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | Project Development is completed and accepted. |  |  | 1 | Lead: Becky, Sundae ¦ Partner: Nef | Project Development |  | 18 | 153 | M01-A08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S01 | M01-A09 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Becky, Sundae and Nef confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for Project Development. |  |  | 1 | Lead: Becky, Sundae ¦ Partner: Nef | Project Development |  | 1 | 154 | M01-A08 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S02 | M01-A09 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for Project Development are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Project Development |  | 1 | 155 | M01-A09-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S03 | M01-A09 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Project Development workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 156 | M01-A09-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S04 | M01-A09 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Project Development workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 157 | M01-A09-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S05 | M01-A09 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Project Development workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 158 | M01-A09-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S06 | M01-A09 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Project Development workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 159 | M01-A09-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S07 | M01-A09 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Project Development workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 160 | M01-A09-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S08 | M01-A09 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Project Development workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 161 | M01-A09-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S09 | M01-A09 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Project Development workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 162 | M01-A09-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S10 | M01-A09 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Project Development workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 163 | M01-A09-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S11 | M01-A09 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Project Development workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 164 | M01-A09-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S12 | M01-A09 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Project Development workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 165 | M01-A09-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S13 | M01-A09 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Project Development workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 166 | M01-A09-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S14 | M01-A09 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for Project Development are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 167 | M01-A09-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S15 | M01-A09 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for Project Development meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 168 | M01-A09-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S16 | M01-A09 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The Project Development release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 169 | M01-A09-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S17 | M01-A09 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative Project Development scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Becky, Sundae ¦ Partner: Nef / Key Users | Project Development |  | 1 | 170 | M01-A09-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A09-S18 | M01-A09 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The Project Development workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Project Development |  | 1 | 171 | M01-A09-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10 |  | Equipment Planning | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | Equipment Planning is completed and accepted. |  |  | 1 | Lead: Becky, Sundae ¦ Partner: Grace | Facilities Management |  | 18 | 172 | M01-A09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S01 | M01-A10 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Becky, Sundae and Grace confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for Equipment Planning. |  |  | 1 | Lead: Becky, Sundae ¦ Partner: Grace | Facilities Management |  | 1 | 173 | M01-A09 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S02 | M01-A10 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for Equipment Planning are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Facilities Management |  | 1 | 174 | M01-A10-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S03 | M01-A10 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Equipment Planning workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 175 | M01-A10-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S04 | M01-A10 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Equipment Planning workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 176 | M01-A10-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S05 | M01-A10 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Equipment Planning workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 177 | M01-A10-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S06 | M01-A10 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Equipment Planning workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 178 | M01-A10-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S07 | M01-A10 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Equipment Planning workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 179 | M01-A10-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S08 | M01-A10 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Equipment Planning workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 180 | M01-A10-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S09 | M01-A10 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Equipment Planning workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 181 | M01-A10-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S10 | M01-A10 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Equipment Planning workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 182 | M01-A10-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S11 | M01-A10 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Equipment Planning workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 183 | M01-A10-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S12 | M01-A10 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Equipment Planning workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 184 | M01-A10-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S13 | M01-A10 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Equipment Planning workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 185 | M01-A10-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S14 | M01-A10 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for Equipment Planning are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 186 | M01-A10-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S15 | M01-A10 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for Equipment Planning meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 187 | M01-A10-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S16 | M01-A10 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The Equipment Planning release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 188 | M01-A10-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S17 | M01-A10 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative Equipment Planning scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Becky, Sundae ¦ Partner: Grace / Key Users | Facilities Management |  | 1 | 189 | M01-A10-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A10-S18 | M01-A10 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The Equipment Planning workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Facilities Management |  | 1 | 190 | M01-A10-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11 |  | DBS Importation | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | DBS Importation is completed and accepted. |  |  | 1 | Lead: Grace ¦ Partner: Pam | CBI / DBS |  | 18 | 191 | M01-A10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S01 | M01-A11 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Grace and Pam confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for DBS Importation. |  |  | 1 | Lead: Grace ¦ Partner: Pam | CBI / DBS |  | 1 | 192 | M01-A10 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S02 | M01-A11 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for DBS Importation are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | CBI / DBS |  | 1 | 193 | M01-A11-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S03 | M01-A11 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the DBS Importation workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 194 | M01-A11-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S04 | M01-A11 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the DBS Importation workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 195 | M01-A11-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S05 | M01-A11 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the DBS Importation workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 196 | M01-A11-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S06 | M01-A11 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the DBS Importation workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 197 | M01-A11-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S07 | M01-A11 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the DBS Importation workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 198 | M01-A11-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S08 | M01-A11 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the DBS Importation workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 199 | M01-A11-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S09 | M01-A11 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the DBS Importation workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 200 | M01-A11-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S10 | M01-A11 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the DBS Importation workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 201 | M01-A11-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S11 | M01-A11 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the DBS Importation workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 202 | M01-A11-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S12 | M01-A11 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the DBS Importation workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 203 | M01-A11-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S13 | M01-A11 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the DBS Importation workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 204 | M01-A11-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S14 | M01-A11 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for DBS Importation are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 205 | M01-A11-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S15 | M01-A11 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for DBS Importation meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 206 | M01-A11-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S16 | M01-A11 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The DBS Importation release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 207 | M01-A11-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S17 | M01-A11 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative DBS Importation scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Grace ¦ Partner: Pam / Key Users | CBI / DBS |  | 1 | 208 | M01-A11-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A11-S18 | M01-A11 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The DBS Importation workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | CBI / DBS |  | 1 | 209 | M01-A11-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12 |  | Manpower Planning and Employee Experience | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | Manpower Planning and Employee Experience is completed and accepted. |  |  | 1 | Lead: Daphne ¦ Partner: Sundae | People and Organization |  | 18 | 210 | M01-A11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S01 | M01-A12 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Daphne and Sundae confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for Manpower Planning and Employee Experience. |  |  | 1 | Lead: Daphne ¦ Partner: Sundae | People and Organization |  | 1 | 211 | M01-A11 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S02 | M01-A12 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for Manpower Planning and Employee Experience are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | People and Organization |  | 1 | 212 | M01-A12-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S03 | M01-A12 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Manpower Planning and Employee Experience workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 213 | M01-A12-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S04 | M01-A12 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Manpower Planning and Employee Experience workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 214 | M01-A12-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S05 | M01-A12 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Manpower Planning and Employee Experience workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 215 | M01-A12-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S06 | M01-A12 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Manpower Planning and Employee Experience workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 216 | M01-A12-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S07 | M01-A12 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Manpower Planning and Employee Experience workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 217 | M01-A12-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S08 | M01-A12 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Manpower Planning and Employee Experience workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 218 | M01-A12-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S09 | M01-A12 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Manpower Planning and Employee Experience workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 219 | M01-A12-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S10 | M01-A12 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Manpower Planning and Employee Experience workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 220 | M01-A12-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S11 | M01-A12 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Manpower Planning and Employee Experience workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 221 | M01-A12-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S12 | M01-A12 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Manpower Planning and Employee Experience workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 222 | M01-A12-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S13 | M01-A12 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Manpower Planning and Employee Experience workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 223 | M01-A12-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S14 | M01-A12 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for Manpower Planning and Employee Experience are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 224 | M01-A12-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S15 | M01-A12 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for Manpower Planning and Employee Experience meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 225 | M01-A12-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S16 | M01-A12 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The Manpower Planning and Employee Experience release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 226 | M01-A12-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S17 | M01-A12 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative Manpower Planning and Employee Experience scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Daphne ¦ Partner: Sundae / Key Users | People and Organization |  | 1 | 227 | M01-A12-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A12-S18 | M01-A12 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The Manpower Planning and Employee Experience workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | People and Organization |  | 1 | 228 | M01-A12-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13 |  | OWD and Foundational Training Initiatives | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 |  | OWD and Foundational Training Initiatives is completed and accepted. |  |  | 1 | Lead: Mich C ¦ Partner: Kim | Organizational Wellness & Development |  | 18 | 229 | M01-A12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S01 | M01-A13 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Mich C and Kim confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for OWD and Foundational Training Initiatives. |  |  | 1 | Lead: Mich C ¦ Partner: Kim | Organizational Wellness & Development |  | 1 | 230 | M01-A12 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S02 | M01-A13 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for OWD and Foundational Training Initiatives are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Organizational Wellness & Development |  | 1 | 231 | M01-A13-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S03 | M01-A13 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the OWD and Foundational Training Initiatives workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 232 | M01-A13-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S04 | M01-A13 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the OWD and Foundational Training Initiatives workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 233 | M01-A13-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S05 | M01-A13 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the OWD and Foundational Training Initiatives workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 234 | M01-A13-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S06 | M01-A13 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the OWD and Foundational Training Initiatives workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 235 | M01-A13-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S07 | M01-A13 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the OWD and Foundational Training Initiatives workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 236 | M01-A13-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S08 | M01-A13 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the OWD and Foundational Training Initiatives workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 237 | M01-A13-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S09 | M01-A13 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the OWD and Foundational Training Initiatives workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 238 | M01-A13-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S10 | M01-A13 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the OWD and Foundational Training Initiatives workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 239 | M01-A13-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S11 | M01-A13 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the OWD and Foundational Training Initiatives workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 240 | M01-A13-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S12 | M01-A13 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the OWD and Foundational Training Initiatives workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 241 | M01-A13-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S13 | M01-A13 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the OWD and Foundational Training Initiatives workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 242 | M01-A13-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S14 | M01-A13 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Acceptance-ready stories for OWD and Foundational Training Initiatives are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 243 | M01-A13-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S15 | M01-A13 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for OWD and Foundational Training Initiatives meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 244 | M01-A13-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S16 | M01-A13 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | The OWD and Foundational Training Initiatives release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 245 | M01-A13-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S17 | M01-A13 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.55 | Applicable departments complete representative OWD and Foundational Training Initiatives scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Mich C ¦ Partner: Kim / Key Users | Organizational Wellness & Development |  | 1 | 246 | M01-A13-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A13-S18 | M01-A13 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.14 | 5.65 | The OWD and Foundational Training Initiatives workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Organizational Wellness & Development |  | 1 | 247 | M01-A13-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14 |  | Leadership Development Initiatives | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 |  | Leadership Development Initiatives is completed and accepted. |  |  | 1 | Lead: Mich V ¦ Partner: Anna | Leadership Development |  | 18 | 248 | M01-A13 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S01 | M01-A14 | Confirm lead, partner, scope, KPIs, and implementation outcome | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Mich V and Anna confirm the accountable roles, scope, measurable KPIs, exclusions, and intended LINK HUB outcome for Leadership Development Initiatives. |  |  | 1 | Lead: Mich V ¦ Partner: Anna | Leadership Development |  | 1 | 249 | M01-A13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S02 | M01-A14 | Document current process and approve target LINK HUB workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | The as-is process, controls, exceptions, hand-offs, target workflow, and approval rules for Leadership Development Initiatives are documented and accepted. |  |  | 1 | Business Analyst / Process Owner | Leadership Development |  | 1 | 250 | M01-A14-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S03 | M01-A14 | BD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Business Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Leadership Development Initiatives workflow in LINK HUB. |  |  | 1 | BD Process Representative | Business Development |  | 1 | 251 | M01-A14-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S04 | M01-A14 | PD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Project Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Leadership Development Initiatives workflow in LINK HUB. |  |  | 1 | PD Process Representative | Project Development |  | 1 | 252 | M01-A14-S03 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S05 | M01-A14 | FM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Facilities Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Leadership Development Initiatives workflow in LINK HUB. |  |  | 1 | FM Process Representative | Facilities Management |  | 1 | 253 | M01-A14-S04 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S06 | M01-A14 | Marketing readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Marketing records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Leadership Development Initiatives workflow in LINK HUB. |  |  | 1 | Marketing Process Representative | Marketing |  | 1 | 254 | M01-A14-S05 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S07 | M01-A14 | P&O readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | People and Organization records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Leadership Development Initiatives workflow in LINK HUB. |  |  | 1 | P&O Process Representative | People and Organization |  | 1 | 255 | M01-A14-S06 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S08 | M01-A14 | OWD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Organizational Wellness & Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Leadership Development Initiatives workflow in LINK HUB. |  |  | 1 | OWD Process Representative | Organizational Wellness & Development |  | 1 | 256 | M01-A14-S07 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S09 | M01-A14 | LD readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Leadership Development records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Leadership Development Initiatives workflow in LINK HUB. |  |  | 1 | LD Process Representative | Leadership Development |  | 1 | 257 | M01-A14-S08 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S10 | M01-A14 | SCM readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Supply Chain Management records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Leadership Development Initiatives workflow in LINK HUB. |  |  | 1 | SCM Process Representative | Supply Chain Management |  | 1 | 258 | M01-A14-S09 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S11 | M01-A14 | F&A readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Finance and Accounting records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Leadership Development Initiatives workflow in LINK HUB. |  |  | 1 | F&A Process Representative | Finance and Accounting |  | 1 | 259 | M01-A14-S10 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S12 | M01-A14 | CBI / DBS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | CBI / DBS records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Leadership Development Initiatives workflow in LINK HUB. |  |  | 1 | CBI / DBS Process Representative | CBI / DBS |  | 1 | 260 | M01-A14-S11 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S13 | M01-A14 | TAS readiness and process checkpoint | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Technology and Solutions records its owner, status or target week, requirements, dependencies, evidence, and approval decision for the Leadership Development Initiatives workflow in LINK HUB. |  |  | 1 | TAS Process Representative | Technology and Solutions |  | 1 | 261 | M01-A14-S12 | Yes
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S14 | M01-A14 | Refine backlog and approve sprint and release plan | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Acceptance-ready stories for Leadership Development Initiatives are prioritized, estimated, assigned to sprints, and linked to an approved LINK HUB release plan. |  |  | 1 | Product Owner / Scrum Team | Technology and Solutions |  | 1 | 262 | M01-A14-S13 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S15 | M01-A14 | Configure and build the LINK HUB process workflow | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Forms, routing, approvals, SLA rules, notifications, permissions, audit trail, reports, and required integrations for Leadership Development Initiatives meet the approved stories. |  |  | 1 | LINK HUB Development Team | Technology and Solutions |  | 1 | 263 | M01-A14-S14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S16 | M01-A14 | Complete QA, security, integration, and regression testing | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | The Leadership Development Initiatives release scope passes functional, permission, audit, integration, security, exception-path, and regression tests without a release blocker. |  |  | 1 | QA Team / TAS | Technology and Solutions |  | 1 | 264 | M01-A14-S15 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S17 | M01-A14 | Conduct cross-department UAT and close findings | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.55 | Applicable departments complete representative Leadership Development Initiatives scenarios, blocking findings are resolved, and the lead and partner approve UAT exit. |  |  | 1 | Lead: Mich V ¦ Partner: Anna / Key Users | Leadership Development |  | 1 | 265 | M01-A14-S16 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M01-A14-S18 | M01-A14 | Release, train users, monitor adoption, and close hypercare | Standard | All Departments' Process Implementation in LINK HUB | 1 | 50 | 7.18 | 5.65 | The Leadership Development Initiatives workflow is deployed to LINK HUB, users receive SOP and training, adoption and KPI results are monitored, and the process owner accepts operational handover. |  |  | 1 | Release Manager / Process Owner | Leadership Development |  | 1 | 266 | M01-A14-S17 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A01 |  | Request for ID | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 |  | Request for ID is completed and accepted. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 4 | 267 | M01-A14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A01-S01 | M02-A01 | Confirm form fields, eligibility, and business rules | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Process owner approves the request data, validations, and requester eligibility. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 268 | M01-A14 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A01-S02 | M02-A01 | Configure approvals, SLA, routing, and notifications | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | The request follows approved routing, timing, and notification rules. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 269 | M02-A01-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A01-S03 | M02-A01 | Test permissions, attachments, and exception paths | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Authorized scenarios pass and unauthorized access is rejected. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 270 | M02-A01-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A01-S04 | M02-A01 | Conduct UAT, publish form, and obtain acceptance | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Business UAT passes and the process owner accepts the published form. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 271 | M02-A01-S03 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A02 |  | Request for Name Plate | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 |  | Request for Name Plate is completed and accepted. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 4 | 272 | M02-A01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A02-S01 | M02-A02 | Confirm form fields, eligibility, and business rules | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Process owner approves the request data, validations, and requester eligibility. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 273 | M02-A01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A02-S02 | M02-A02 | Configure approvals, SLA, routing, and notifications | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | The request follows approved routing, timing, and notification rules. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 274 | M02-A02-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A02-S03 | M02-A02 | Test permissions, attachments, and exception paths | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Authorized scenarios pass and unauthorized access is rejected. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 275 | M02-A02-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A02-S04 | M02-A02 | Conduct UAT, publish form, and obtain acceptance | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Business UAT passes and the process owner accepts the published form. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 276 | M02-A02-S03 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A03 |  | Request for Uniform | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 |  | Request for Uniform is completed and accepted. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 4 | 277 | M02-A02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A03-S01 | M02-A03 | Confirm form fields, eligibility, and business rules | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Process owner approves the request data, validations, and requester eligibility. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 278 | M02-A02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A03-S02 | M02-A03 | Configure approvals, SLA, routing, and notifications | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | The request follows approved routing, timing, and notification rules. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 279 | M02-A03-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A03-S03 | M02-A03 | Test permissions, attachments, and exception paths | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Authorized scenarios pass and unauthorized access is rejected. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 280 | M02-A03-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A03-S04 | M02-A03 | Conduct UAT, publish form, and obtain acceptance | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Business UAT passes and the process owner accepts the published form. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 281 | M02-A03-S03 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A04 |  | Request for Globe Postpaid Plan | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 |  | Request for Globe Postpaid Plan is completed and accepted. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 4 | 282 | M02-A03 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A04-S01 | M02-A04 | Confirm form fields, eligibility, and business rules | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Process owner approves the request data, validations, and requester eligibility. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 283 | M02-A03 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A04-S02 | M02-A04 | Configure approvals, SLA, routing, and notifications | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | The request follows approved routing, timing, and notification rules. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 284 | M02-A04-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A04-S03 | M02-A04 | Test permissions, attachments, and exception paths | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Authorized scenarios pass and unauthorized access is rejected. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 285 | M02-A04-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A04-S04 | M02-A04 | Conduct UAT, publish form, and obtain acceptance | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Business UAT passes and the process owner accepts the published form. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 286 | M02-A04-S03 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A05 |  | Request for Employee Sale | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 |  | Request for Employee Sale is completed and accepted. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 4 | 287 | M02-A04 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A05-S01 | M02-A05 | Confirm form fields, eligibility, and business rules | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Process owner approves the request data, validations, and requester eligibility. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 288 | M02-A04 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A05-S02 | M02-A05 | Configure approvals, SLA, routing, and notifications | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | The request follows approved routing, timing, and notification rules. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 289 | M02-A05-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A05-S03 | M02-A05 | Test permissions, attachments, and exception paths | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Authorized scenarios pass and unauthorized access is rejected. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 290 | M02-A05-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A05-S04 | M02-A05 | Conduct UAT, publish form, and obtain acceptance | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Business UAT passes and the process owner accepts the published form. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 291 | M02-A05-S03 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A06 |  | Vehicle Repairs and Maintenance | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 |  | Vehicle Repairs and Maintenance is completed and accepted. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 4 | 292 | M02-A05 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A06-S01 | M02-A06 | Confirm form fields, eligibility, and business rules | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Process owner approves the request data, validations, and requester eligibility. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 293 | M02-A05 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A06-S02 | M02-A06 | Configure approvals, SLA, routing, and notifications | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | The request follows approved routing, timing, and notification rules. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 294 | M02-A06-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A06-S03 | M02-A06 | Test permissions, attachments, and exception paths | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Authorized scenarios pass and unauthorized access is rejected. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 295 | M02-A06-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A06-S04 | M02-A06 | Conduct UAT, publish form, and obtain acceptance | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Business UAT passes and the process owner accepts the published form. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 296 | M02-A06-S03 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A07 |  | Security Guard Concerns | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 |  | Security Guard Concerns is completed and accepted. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 4 | 297 | M02-A06 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A07-S01 | M02-A07 | Confirm form fields, eligibility, and business rules | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Process owner approves the request data, validations, and requester eligibility. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 298 | M02-A06 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A07-S02 | M02-A07 | Configure approvals, SLA, routing, and notifications | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | The request follows approved routing, timing, and notification rules. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 299 | M02-A07-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A07-S03 | M02-A07 | Test permissions, attachments, and exception paths | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Authorized scenarios pass and unauthorized access is rejected. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 300 | M02-A07-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A07-S04 | M02-A07 | Conduct UAT, publish form, and obtain acceptance | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Business UAT passes and the process owner accepts the published form. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 301 | M02-A07-S03 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A08 |  | Flight Accommodations | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 |  | Flight Accommodations is completed and accepted. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 4 | 302 | M02-A07 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A08-S01 | M02-A08 | Confirm form fields, eligibility, and business rules | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Process owner approves the request data, validations, and requester eligibility. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 303 | M02-A07 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A08-S02 | M02-A08 | Configure approvals, SLA, routing, and notifications | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | The request follows approved routing, timing, and notification rules. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 304 | M02-A08-S01 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A08-S03 | M02-A08 | Test permissions, attachments, and exception paths | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Authorized scenarios pass and unauthorized access is rejected. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 305 | M02-A08-S02 | No
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI |  | LINK HUB | Both | M02-A08-S04 | M02-A08 | Conduct UAT, publish form, and obtain acceptance | Standard | P&O Employee Services Agreed Forms | 2 | 50 | 12.5 | 25 | Business UAT passes and the process owner accepts the published form. |  |  | 1 | P&O Process Owner / LINK HUB Team |  |  | 1 | 306 | M02-A08-S03 | No

## Template Index
Included Hybrid SDLC / Agile Templates
Template Name | Project Type | Entity | Brand | Project Name | Milestones | Import Rows
TGI - LINK HUB | Corporate Group: Servicing Brand | TGI | — | LINK HUB | 2 | 306

## Collaboration Matrix
Group | Process | Lead | Partner | BD | PD | FM | Marketing | P&O | OWD | LD | SCM | F&A | CBI / DBS | TAS
1 | New Store Opening | Pam | Daphne | Milestone | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting
1 | Store Closure | Pam | Daphne | Milestone | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting
1 | Store Renovation | Pam | Daphne | Waiting | Milestone | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting
2 | Requisition Process | Cel | Brendan | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Milestone | Waiting | Waiting | Waiting
2 | Purchasing Process | Cel | Brendan | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Milestone | Waiting | Waiting | Waiting
2 | Procure to Pay | Anna, Rach | Becky | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Milestone | Waiting | Waiting
3 | Campaign Launch | Kim, Josie | Rach | Waiting | Waiting | Waiting | Milestone | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting
3 | Product Launch | Kim, Josie | Cel | Waiting | Waiting | Waiting | Milestone | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting
4 | Project Development | Becky, Sundae | Nef | Waiting | Milestone | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting
4 | Equipment Planning | Becky, Sundae | Grace | Waiting | Waiting | Milestone | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting
4 | DBS Importation | Grace | Pam | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Milestone | Waiting
5 | Manpower Planning and Employee Experience | Daphne | Sundae | Waiting | Waiting | Waiting | Waiting | Milestone | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting
5 | OWD and Foundational Training Initiatives | Mich C | Kim | Waiting | Waiting | Waiting | Waiting | Waiting | Milestone | Waiting | Waiting | Waiting | Waiting | Waiting
5 | Leadership Development Initiatives | Mich V | Anna | Waiting | Waiting | Waiting | Waiting | Waiting | Waiting | Milestone | Waiting | Waiting | Waiting | Waiting

## Instructions
Hybrid SDLC / Agile Activity Template Instructions
Purpose | Recommended starting structures for the listed application projects. Review owners, durations, dependencies, weights, and acceptance criteria before importing.
Import | Open Activity Templates, choose Import, and upload this XLSX. The application groups rows by Template Name, Project Type, and Store Class.
Project Name | DAVID, LINK HUB, DIWA, and LINK PORTAL remain plain-text Project Name values; there is no Solution dropdown.
Hierarchy | Milestone = business capability or release; Activity = SDLC phase, sprint, or store rollout; Sub-Task = assignable accepted deliverable.
All Departments | All Departments' Process Implementation in LINK HUB contains one Activity per business process. Its Sub-Tasks cover department readiness plus the hybrid SDLC / Agile work needed to implement, test, release, and adopt that process in LINK HUB.
Collaboration Matrix | Use the matrix as the cross-department reporting view. Milestone marks the primary owning department and Waiting is the recommended initial state; replace these with current status or target week as planning progresses. Imported Sub-Tasks remain the source of progress percentages.
Parallel planning | Independent departmental readiness checkpoints run in parallel after the target workflow is approved. LINK HUB business processes also run as parallel workstreams; design/build/QA/UAT/release gates inside each process remain sequential.
Task Board | Keep detailed user stories, bugs, and developer tasks on the Task Board. The Gantt should track accepted sprint/release outcomes.
Weights | Milestones total 100% per template, activities total 100% per milestone, and sub-tasks total 100% per activity.
Per Store | A Per Store activity is cloned after target stores are selected. Do not manually create 35 placeholder store rows.
NONOS DIWA | 35 is the recommended target-store count. The workbook does not create store assignments.
CBTL DIWA | Target-store count remains to be confirmed.
Safety | Import into a test environment first. Re-importing an identical template is skipped rather than overwriting it.

## WBS Guide
Work-Breakdown Guide
Level | Use | Example | Progress rule
Project | One application in one entity/brand context | DAVID · TGI · CBTL | Weighted milestone roll-up
Milestone | Business capability, release, or rollout outcome | Inventory Scanning with Barcode Scanner | Weighted activity roll-up
Activity | SDLC phase, Agile sprint, or per-store deployment | Sprint 1 – Core Workflow | Weighted sub-task roll-up
Sub-Task | Concrete deliverable with acceptance criteria | Product owner accepts sprint demo | Owner updates 0–100%
Task Board | Stories, bugs, coding tasks, and daily execution | API validation bug | Feeds its linked Gantt deliverable

## Lists (hidden)
Project Types | Entity Codes | Brand Codes | Store Classes | Activity Modes | Yes / No
Full Service Group: Customer Brand | TGI | NONOS | Regular | Standard | No
Corporate Group: Servicing Brand | GSI | CBTL | Kitchen | Per Store | Yes
| NCF | DSY | Both
DBS